## Schedule
Deployment Plan |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13
|  | 2025-02-14 | 2025-02-21 | 2025-02-28 | 2025-03-07 | 2025-03-14 | 2025-03-21 | 2025-03-28 | 2025-04-04 | 2025-04-11 | 2025-04-18 | 2025-04-25 | 2025-05-02 | 2025-05-09
Case for Change
Set Goals for Project | Agree KPIs to improve / how to measure
(normally pre-deployment) | Document & quantify cost of key pain points / bottlenecks
Root cause analysis: identify underlying drivers of pain points
Identify key stakeholders & their goals
Build a Plan | Define 90-day priorities plus goals for later phases
Determine scope (from components below) & phasing - they are not sequential
Strategic Planning
Determine the Scope | Clarify the base (Vision & Mission) that will form the basis of the bridge (modelling with TCH) to understand start point
What will be covered? Strategic Initiatives, Continuous Improvement, Product Development, BAU work?
Determine delegation for Scenrio Building: Semi-autonymous divisions vs. pure top-down
Detail Reporting needs (Time Period + P&L structure + metric based reporting)
Plan Deployment | Select steps as required from -Demand Management / Project Prioritization / Business Case / Capacity Planning - below
Scope the pivot from Strategic Plan to Portfolio Management to maximize long term impact
Demand Management
Process Mapping | Review the As Is Process Map - identify pain points, best practice gaps & opportunities to improve in software
Draft To-Be Process Map with roles, workflows, authority levels & change requests agreed
Front Door | Audit current tooling / source of data
Decide how to collect data (import, connector, request page or manual)
Stage Gating | Understand To Be process for project selection inc. Stage Gates
Define target Business Case approach - e.g. simple data collection vs. funded research into options
Identify decision making processes to support - e.g. budget allocation, monthly governance, annual planning etc
Sign-off Kanban steps & definitions
Scope & Structure | Decide Portfolio Structure: One value model vs. many
Value Model - one for all or one for each portfolio?
Other Models (Effort, Risk, Mandatory & Urgency)
Agree overall flow of work (e.g. what comes first, Business Case vs. Scoring)
Project Prioritization
Explore Goals | Collect strategy documents
(replicate for each model) | Collect pros & cons for projects
Interview key stakeholders (get from case for change if this is already clear)
Build Model(s) | Build & Iterate Strawmen models
Test Pairwise & score sample projects
Finalise Criteria | Sponsor sign-off
Document definitions
Add scales (inc. hard data feed, see section below)
Leadership Review | Pairwise survey + Criteria Weights Workshop
Repeat for local models / risk model with appropriate audience
Document models as key value point
Engage People | Identify Workspace + Business Users to add into software
Set up training to support their on-boarding (NB this may be aligned to Business Case submission based on flow)
Add Projects | Generate new candidate projects for consideration
Include WIP & BAU where there is potential to stop
Add dependencies between projects
Score Projects | Assign SME experts & send surveys
Arrange workshops to review disagreements
Capture detailed Risks / Benefits to feed into Business Case
Stage Gate 1 triage: remove the weakest candidates (subject to the process you identify in the plan)
Build Business Case
Scope of Business Case | Simple data vs. detailed review of Options
Explore role for AHP support to key in-project decisions (optional, likely post-MVP)
Document As Is ask for data collection to minimize duplication
Decide on format / solution / level of detail for data collection (e.g. TCH + Sharepoint)
Define Benefits + Risks | Types of revenue to model
(set up template for data capture) | Other 'hard benefits' to capture
Link to criteria model where appropriate
Capture Risks / Benefits
Resource Capacity & Financial Constraints | Determine resources for capacity planning ('pots' not people)
(set up template for data capture) | Flag suspected bottleneck areas
Set cost / resource pot for internal value calculations
Determine which Opex & Capex lines to capture
Configuration | Date Settings: Start Date / review period / granularity (month/qtr/year)
(set up template for data capture) | Meta Data: Sponsor / Department etc
Text Fields: Benefits / Extended description etc
Reporting & Metrics required
Engage People | Identify Workspace + Business Users to add into software
(NB this is repeat of Scoring Step) | Set up training to support their on-boarding
Collect Business Cases | Assign Ownership to project leads
(assumes projects added in scoring) | Complete & submit Business Cases (could require additional coaching based on level of change / complexity)
Stage Gate 2 triage: remove projects where business case is weak (subject to the process you identify in the plan)
Build Portfolio Scenario (base case) | Load projects passing Stage Gate 2
Fix selection where project is "must have"
Fix start dates where timeline is non-flexible
Capacity Planning
Set Constraints (resource + £) | Work out Resource limits x month (e.g. back out BAU, internal planning, time off etc)
(Enterprise Scenarios) | Set Capex / Opex limits for the planning horizon
Set Enterprise buffer levels
Consider Portfolio Rebalancing: e.g. BAU vs. Change portfolios
Allocate remainder by portfolio (this can be iterative / flex by Enterprise scenario)
Optimize / Schedule | Optimize all Portfolios to fit within defined constraints
(Iterative with AI tools) | Apply scheduling to stagger start dates at Enterprise Level
Review Portfolios' Strategic Fit - compare back to Criteria Model
Review Benefits - include risk adjusted P&L for assurance
Iterate / Build Scenarios / overlay manual preferences to AI base
Go live | Pick projects to fund / start / reject / stop - look for quick wins
Progress first cohort of projects into Work in Progress status
Portfolio Management (NB Elements of this are in development in TCH)
Governance Set Up | Initiate monthly / quarterly Governance Board
Link terms to Process Map plan
Build Reports required to support Governance Board (in TCH & other sources)
Embed Software | Determine data flow to Project Management tools (e.g. PPM, Excel etc)
Set process for adding new projects
Set process for updating WIP (Risks, Benefits, Burn Down, Change Requests, Post-Approval Stage Gate progression etc)
Set process for updating capacity constraints
Set process for generating Reports (in-built, download, links to Power BI etc)
Drive project flow behaviour | Coach PMs to realize value of being focused on fewer projects
post-MVP scope | Iterate on projects' plans to reduce target duration (e.g. link to lessons learned)
Identify opportunities to address bottlenecks with process re-engineering
Benefits Realization | Review Benefits, Scores & Costs vs. Business Case from Selection stage
post-MVP scope | Survey SMEs for feedback
Identify key lessons learned to feedback into planning
Measure, promote, improve | Collect feedback on areas to iterate
post-MVP scope | Revisit Case for Change to measure progress
Identify quick wins & improved KPIs for internal PR
Challenge areas where old ways of working persist / people are gaming the system
Identify areas to save effort & simplify processes

## 6 Week POC example
Example proposal: 6 week POC
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6
Demand Management
T-Shirt Sizing / Gating | x
Project List with "meta data" in excel - split BAU vs. Change |  | x
Define Front Door / Kanban |  | x | x
Strategic KPIs inc. Revenue + Savings metrics | x
Project Prioritization - Build prototype model
Strategic Plan Stuff (decks / metrics / plans etc) | x
Project Pros & Cons | x
Model preference - Detail vs. high level for Value (Bank / Risk focus) | x
Delivery Risk Model (yes-no) | x
Review Model / add weights |  | x | x
List of project scorers (emails) / Score Projects |  |  | x | x | x
Build Business Case
12-24 months plan / configuration settings |  | x
20 People - Capacity + Estimates at project level + estimated unit cost |  |  | x
Other Project Costs (inc. capital ) |  |  | x
Sign-off Business Case data for 20 projects |  |  |  | x
Capacity Planning
Define Constraints (limits costs/capex/resurces) split x BAU vs. change |  |  |  |  | x
Build Scenarios / Reports |  |  |  |  | x | x