## Define the Team
Build the Team Identify who needs to be part of a successful deployment
| Role | Description | Profile
Core | Decision Science Facilitator | Manage meetings to complete weights + scoring, advise the methodology, support final review process | Ideally external support for expertise + objective point of view
| Software Super User | Main admin user of the software, configuring settings, generating surveys, reports etc | Ideally internal role with high capacity to dedicate time during deployment
| Project Lead | Leads change management process, driving alignment with current processes, managing data integrations etc | Must be internal - a PMO or change management lead who know the organization (aka "cat herder in chief")
| Executive Sponsor | Oversight for project success, ensuring stakeholder alignment | Key role - able to make decisions on the model, processes and drive resource allocation once the data is available
Extended | Executive Stakeholders | Define policy via criteria & weights, support teams to get behind scoring | Light touch only, but important to build alignment to use AHP
| Subject Matter Experts (SMEs) | Deep knowledge of one or more criteria, responsible for voting on projects | Key to scoring, use targeting to match knowledge to criteria efficiently so don't use up too much time

## Deployment Guide -->
Deployment Guide Successful Delivery Step by Step

## Make A Plan
Make a Plan
|  |  | Roles | [5 empty] | Notes | Timeline - week starting
| Step | Description | Facilitator | Super User | Project Lead | Sponsor | Execs | SMEs |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Make a Plan | Build internal alignment | Be the internal cheerleader for change - get people excited about working together to unlock HUGE benefits. Pom Poms Optional.
| Strategic Review - identify your starting point | Identify 'how things work round here'. Run through 3 P's. Compile existing strategy docs. Identify what went wrong with your last planning process.
| Split your Portfolio up into buckets | How are you going to prioritize? 1 big bucket, or multiple smaller ones with different criteria?
| Get the team together | Identify who to involve: from the Super User to the Execs. Make sure they're ready for what comes next.
| Build a plan | Use Deployment Guide to help build your own plan. Knit together diaries, deadlines and bandwidth to set yourself up to win.
| Get training | Go to Client Hub for videos and guides & book training meetings for zoom based support sessions. Start your journey to Jedi prioritizer.

## Build AHP Model
Build AHP Model
|  |  | Roles | [5 empty] | Notes | Timeline - week starting
| Step | Description | Facilitator | Super User | Project Lead | Sponsor | Execs | SMEs |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Build Criteria | Sign-off portfolio strategy | Make sure the goalposts are in place. Determine the nos of AHP models & their high level goals.
| Use current review documents as a base for drafting criteria. | Look at current portfolio for 'pros & cons' review. Compile existing strategy docs / scorecards for high level company goals.
| Deep Dive AHP Best Practice | Does the '5 bucket model' apply? What is a Criteria vs. Not a Criteria? Check criteria for common mistakes to avoid pitfalls.
| Build Criteria in Software | Load in draft Criteria - final sign off will be after measurements are added + pairwise checked.
| Add Measurement Scales | Use Measurement page to add scales (NB these will generate Attributes automatically). Consulting SMEs can be useful.
Criteria Weights | Final Sign-Off for Criteria + Scales | The AHP model is now fixed - changing beyond this point will involve repeating steps below.
| Load People & mail out links | Load data into People section, then mail our Pairwise Survey to Execs. Support with Respondents Guide (available on the "i" button in the survey).
| Meet to Review - real time alignment | Prepare by checking disagreements. Get people together, Set Opinion Panel to Meeting Mode, and use Real Time Voting to align.
| Publish Weights & Weighted score | Save final Weight set. Share data vizualisation. Create Weighted Score so Value Score is automated.
| Create Scenarios (OPTIONAL) | Create alternative Weight Set for different scenarios if required.

## Set Up Software
Set-Up Software
|  |  | Roles | [5 empty] | Notes | Timeline - week starting
| Step | Description | Facilitator | Super User | Project Lead | Sponsor | Execs | SMEs |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Configure Attributes | Getting Started with Data | Work out the data you need, and where you will get it. Use Excel Toolkit to capture plan & make it easy to map into software.
| Attribute Uses (1) Core Data | Add Name and Description - they are built into the software as Attributes.
| Attribute Uses (2) Enrich Description (OPTIONAL) | Add a more extensive Project Description (e.g. Benefits Case), a link to a URL, an image or even a video so Respondents know what a Project is all about.
| Attribute Uses (3) Criteria | Follow AHP best practice in defining scales for Qualitative criteria & MIN-MAX levels for Quantitative criteria.
| Attribute Uses (4) Resource | Defined as either money or people. Collection can be via single source of data OR panel of SMEs.
| Attribute Uses (5) Reporting Hierarchy (OPTIONAL) | Split Reports or Assessments into buckets by tagging projects against (for example) department. Multiple tags supported.
| Attribute Uses (6) Sponsor / PM / roles (OPTIONAL) | Collect emails for key people involved with the Project to enable Notifications to be generated.
| Attribute Uses (7) Targeting (OPTIONAL) | Lock Project Scoring to named Respondents. Can be set up as either import of string of emails OR built from a Form.
| Attribute Uses (8) Other context (OPTIONAL) | Any additional 'tags' that are useful can be added to support either Reporting or Panel building (e.g. flag 'mandatory projects').
| Attribute Uses (9) Value Scores | The output of your model(s) is a 0-100 score for every project that will be saved as an Attribute.
| Attribute Uses (10) Value for Money | Combine Value Score and Resource to generate 'Value' metric. May require scaling factor (e.g. x1000).
Configure Pipeline | Configure Kanban - Labels | Set Labels for naming convention for 'Projects' (e.g. programs / features / alternatives etc).
| Configure Kanban - Stages | Create stages for your decision (e.g. New / Ready to Score) AND outcomes (e.g. Approved / Rejected).
| Data Collection Tools - Forms | Create custom forms for collecting Attribute data - use Mandatory / Read Only settings to manage compliance.
| Data Collection Tools - Notifications (OPTIONAL) | Add triggers to send targeted emails when Kanban status changes.
| Data Collection Tools - To Do Lists (OPTIONAL) | Use Reports section as data collection tool if needed.
| Collect Alternatives - 3 options for loading projects | Review where project data will come from & how to get it into TransparentChoice.
| (1) Data Import | Build project list in Excel (typically as export from system of record) and import directly into the software. Ideal for a mature portfolio.
| (2) Request Page | Set up Request Page for colleagues to click a URL and get access to a Form to add New Projects. Great for ideation.
| (3) Manual Entry | Add projects directly into the Kanban. Quickest solution for small number of Projects.
| Organise Alternatives - Lists | Use Attributes / Kanban Status / Other Lists to create dynamic buckets of programs. These are for Assessment Panels + Reports.
| Organise Alternatives - Other (OPTIONAL) | Explore further configuration options - Kanban views, Dependencies tracking & Decision Log.

## Score & Report
Deploy AHP Model
|  |  | Roles | [5 empty] | Notes | Timeline - week starting
| Step | Description | Facilitator | Super User | Project Lead | Sponsor | Execs | SMEs |  | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8
Score Projects | Pick Scorers - Best Practice | Decide how to approach scoring to minimise noise & get the best knowledge from your colleagues. Allow time for a productive review process.
| Pick Scorers - Configure Assessments & collect survey data from SMEs | Load SMEs into People section, then configure Assessments Panels. Mail out survey links, then chase completion ahead of meeting.
| Collect Data - Meeting Mode + Save | Use Meeting Mode / disagreements identify misalignment. Discuss as a team & align on scores. SAVE panel to complete scoring.
| Review Value Scores (OPTIONAL) | Ranking Page is optional but recommended for 'Pick One' reviews especially.
Report Results | Data Checklist | Make sure you have Value Scores / Project Data / Lists / Value for Money / Kanban Stages done.
| Create Reports - Data Vizualisation | Build & share Reports. Apply settings, then add Metrics, Bar Charts, Scatter Plots & customise project level data.
| Make your Decision | Use Reports to set Kanban Status / Lists - building out a final portfolio to make the best use of resources.
| Build Scenarios (OPTIONAL) | Create alternative portfolios if required to offer different choices. Use Reports to compare outcomes.
| Extract Data (OPTIONAL) | Ad-hoc work outside the software by using Export functions. Download all Attributes from Dashboard view, detailed Criteria scores from Ranking, or Voting data from Assessments.